## Legend
Category-wise steps for confirmed programs
Legend for time-limits within which things need to be done:
Symbol | Meaning | Date | Notes | Milestone
R | stands for date of receiving RFP | 2025-08-01 | Input actual date of receiving RFP | Working on RFP
R+ | stands for no. of days after receiving RFP
S | stands for proposal submission date |  | Input actual deadline of submitting proposal or Actual date of submitting proposal | Working on RFP
S-/+ | stands for no. of days before/after proposal submission date
W | stands for date when client approves our proposal |  | Input actual date when program is won | Planning
C | stands for date of confirmation (for repeat clients, this can be when they tell us group size) | 2025-09-01 | Input actual date of program confirmation | Planning
C+ | stands for no. of days after confirmation/go-ahead received from client
P | stands for program dates | 2025-12-01 | Input actual program start date | Delivery
PE | stands for program end date |  | Input actual program end date | Delivery
P- | stands for no. of days before program start
P+ | stands for no. of days after the program ends

## Faculty Led Programs
Operations Process (Proposal to Delivery)
Action Items while sending proposals
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Ensure sales hand-off template is filled; clarify doubts, if any before working on the proposal | R+1 |  | Working on RFP | Hand-off to ops team
Detail out the requirements and send it to DMCs/Vendors | R+2 |  | Working on RFP | Using draft itinerary template
Create a costing sheet with quotes from DMCs/hotels | R+7 |  | Working on RFP
Complete and review the costing sheet and proposal | R+9 |  | Working on RFP | Use formats like hotel sheet to finalize hotel options
Submit proposal to client | S |  | Working on RFP | Sales team submits the proposal
Block all proposed hotels and guides | S |  | Working on RFP | ensure payments & cancellation are on agreeable terms
Followup with client/sales on the proposal status to release or keep the blocks | S+10 |  | Working on RFP | Proposal confirmation timeline could vary
Action Items after proposal is won
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Sign contracts with hotels and DMCs | W+1 |  | Planning | timeframe could vary
Followup with client/sales on program confirmation date | P-76 |  | Planning | timeframe could vary
Action Items after program confirmation
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Send deposit invoice to university | P-76 |  | Planning | Check proposal terms and conditions
Create mastersheet | C+3 |  | Planning | Use template and fill information on an on-going basis
Set up Monday.com/google sheet for collaboration with all university stakeholders | C+3 |  | Planning | ENHANCED: Real-time tracking
Share participant data template to collect information (including scanned passport copies) | C+7 |  | Planning | Use participant data template #to client
Send balance invoice to university | P-32 |  | Planning
Get confirmation on final service requirements from university | P-32 |  | Planning | Confirm final group size, hotel blocks, transport, guides, meals, academic content and cultural immersions
Send final program services agreement | P-22 |  | Planning
Prepare for in-person/online program orientation and safety briefing | P-22 |  | Planning | Refer to India orientation PPT
Create and share pre-departure guide | P-22 |  | Planning | Refer to standard pre dep template
Create checklist for delivery | P-10 |  | Delivery | Refer to mastersheet for template
Plan and prepare first aid kits and other relevant material specific to programs | P-5 |  | Delivery
Print checklists and relevant documents | P-5 |  | Delivery
Send post program invoice to the university | PE+10 |  | Delivery | Enter Program end date + 7 days
Send thank you notes to partner organizations / companies | PE+5 |  | Delivery | Send thank you notes on the same day of the visit (could vary based on the work load)
Pre-departure planning
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Mandatory vendor service specification documentation | P-22 |  | Planning | NEW: All limitations documented
Complete program orientation for guides and local partners | P-22 |  | Planning | Brief them about Authentica standards
Triple Verification Protocol
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Verify pre-program delivery checklist | P-5 |  | Planning | Refer template
Hotels
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Block and sign contracts with chosen hotels and procure invoices with payment details | W+1 |  | Planning | As per updated numbers received from the university
Release block for other hotels across locations | W+1 |  | Planning
Reconfirm number of rooms after we receive confirmed group size | C+1 |  | Planning
Send advance to chosen hotels: CCA / bank transfer / outward remittance | P-66 |  | Planning | could vary
Collect rooming list from client and send it to hotels | P-15 |  | Delivery
Flight/Train bookings
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm preferred flight/train option with client | P-44 |  | Planning | could vary
Collect participant information / passport scans | P-44 |  | Planning | could vary
Book tickets (either with vendor or directly online) and share tickets with university | P-39 |  | Planning | could vary
Guides
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Book dates of preferred guides (Directly or with DMC) | W+5 |  | Planning
Send draft itinerary to guides/DMC along with the academic objective briefing | P-22 |  | Planning
Send final itinerary / checklist and PAX info to guides | P-10 |  | Delivery | could vary
Meeting Rooms
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm exact requirement from client (preferred venue location, purpose of meeting, group size, AV requirement, F&B etc.) | P-44 |  | Planning
Identify, block and finalize venue | P-39 |  | Planning
Pay advance, if needed | P-22 |  | Planning | could vary
Re-confirm exact requirements from university and share it with vendors | P-10 |  | Delivery
Transport
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm requirement for each destination / specific visits or requirements (e.g. seatbelts, wheelchair acess etc.) and share with vendors/DMC | P-44 |  | Planning
Send transport/DMC itinerary to check about routes, timings or any specific requirements/issues | P-22 |  | Planning
Share arrival and departure schedule to university and share it with vendors/DMC | P-15 |  | Planning | As per the mastersheet template
Send final itinerary and placard | P-10 |  | Planning | Asian DMCs require this earlier
Meals
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm meal requirements to be included | P-44 |  | Planning
Research appropriate options in each destination (if not done already) | P-42 |  | Planning | sometimes we have specific seating requirement
Contact shortlisted venues to get availability, rates and menu details | P-40 |  | Planning
Finalilze and block chosen venues | P-39 |  | Planning | sometimes client approval is needed
Pay advance, if needed | P-22 |  | Planning
Send dietary restrictions | P-22 |  | Planning
Finalize menu with dietary restrictions | P-15 |  | Planning | sometimes client approval is needed
Reconfirm seating and menu | P-1 |  | Delivery
Immersions
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Finalilze and block chosen options with any specific instruction (e.g. specific guides, atomic bomb survivor etc.) | P-44 |  | Planning | sometimes client approval is needed
Pay advance, if needed | P-22 |  | Planning
Org Visits
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Brief PDs/Content partners regarding program theme and requirements | C+1 |  | Planning
Collect relevant info to be shared (e.g. bio book) from client | P-22 |  | Planning
Finalize visits in discussion with the client and PDs | P-22 |  | Planning
Get logistical contacts from PDs at for each visit | P-22 |  | Planning
Co-ordinate with organizations about the visit (timings, address, meals, security protocols like passports, roster sheet, license plate) | P-10 |  | Planning
Plan and procure gifts for organization visits | P-22 |  | Planning
Post Program Action items
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Send post program invoice to the university | PE+10 |  | Delivery | Enter Program end date + 7 days
Send thank you notes to partner organizations / companies | PE+5 |  | Delivery | Send thank you notes on the same day of the visit (could vary based on the work load)
Settle balance payments of all vendors | PE+10 |  | Delivery
Submit expense report to HQ | PE+10 |  | Delivery
Upload media to zoho drive | PE+10 |  | Delivery
Service failure compensation processing | PE+15 |  | Delivery | NEW: Proactive client relations
Local partner performance evaluation | PE+15 |  | Delivery | NEW: Continuous improvement
Process improvement documentation | PE+15 |  | Delivery | Use learnings template in Mastersheet
Debrief with all stakeholders | PE+22 |  | Delivery | NEW: Rapid issue identification
Document Version History
Modified By | Created on | Modified On |  | Comments | Version #
Siddhanth Waghmare | 2025-01-22 | 2025-01-22 |  | Updated a checklist for End-To-End Operations Process (Proposal to Delivery); created excel sheet from Monday board (Operations Process) | 1
Siddhanth Waghmare | - | 2025-07-07 |  | This upgraded checklist incorporates specific learnings from the Ohio State KSA Spain and JADE programs to prevent recurrence of identified issues while maintaining operational excellence. | 2
Sid, Vedanth and VL |  | 2026-03-24 |  | Modified the list for specific action oriented goals. Separated action items Vs quality checklist | 3
Sid, Vedanth and VL |  | 2026-04-22 |  | Updated timelines of all action items. Added a new milestone "W" | 4
Note on E122: Siddhanth Waghmare: KEY SYSTEM ENHANCEMENTS 1. Booking Management System • Triple verification protocol for all reservations • Automated alerts for enrollment changes • Screenshot confirmation requirements • Penalty clauses in vendor contracts 2. Communication Framework • Mandatory 72-hour vendor briefings • Monday.com real-time collaboration • Written confirmation protocols • Local language documentation requirements 3. Quality Assurance Protocol • 52-point pre-departure checklist • Daily operations monitoring • Service failure compensation framework • Continuous improvement documentation 4. Emergency Response Enhancement • Weather contingency planning • Emergency transportation budget • Immediate escalation procedures • 24/7 management access ________________________________________ COMPLIANCE CHECKPOINTS New Mandatory Checkpoints Based on OSU Issues: ✓ Accommodation Standards Verification • Private bathroom confirmation • Accessibility compliance • Group cohesion maintenance ✓ Transportation Coordination • Driver briefing completion • Safety protocol acknowledgment • Itinerary delivery confirmation ✓ Vendor Service Specifications • Size/weight limitations documented • Service restrictions communicated • Academic objectives clarified ✓ Timeline Management • Deliverable scheduling verification • Weather contingency activation • Change request protocol adherence