## Legend
Program Name | 2026-10 India Pilot Program Test
Owner | Siddhanth Waghmare
Symbol | Meaning | Date | Notes | Milestone
Siddhanth Waghmare
R | stands for date of receiving RFP | 2025-08-01 | Input actual date of receiving RFP | Working on RFP
R+ | stands for no. of days after receiving RFP
S | stands for proposal submission date | 2025-08-15 | Input actual deadline of submitting proposal or Actual date of submitting proposal | Working on RFP
S-/+ | stands for no. of days before/after proposal submission date
C | stands for date of confirmation (for repeat clients, this can be when they tell us group size) | 2025-09-01 | Input actual date of program confirmation | Planning
C+ | stands for no. of days after confirmation/go-ahead received from client
P | stands for program dates | 2025-12-01 | Input actual program start date | Delivery
PE | stands for program end date | 2025-12-12 | Input actual program end date | Delivery
P- | stands for no. of days before program start
P+ | stands for no. of days after the program ends

## Sample Data
Operations Process (Proposal to Delivery)
Hotels
Name | Due Date | Owner | Notes | Process # | Timeline - Start | Timeline - End
Block and sign contracts with chosen hotels and procure invoices with payment details | 2025-09-02 | Siddhanth Waghmare | As per updated numbers received from the university
Release block for other hotels across locations | 2025-09-02 | Siddhanth Waghmare
Send advance to chosen hotels: CCA / bank transfer / outward remittance | 2025-10-01 | Siddhanth Waghmare | could vary
Collect rooming list from client and send it to hotels | 2025-11-16 | Siddhanth Waghmare
Flights
Name | Due Date | Owner | Notes | Process # | Timeline - Start | Timeline - End
Confirm preferred flight/train option with client | 2025-09-02 | Siddhanth Waghmare | could vary
Collect participant information / passport scans | 2025-09-08 | Siddhanth Waghmare | could vary
Book tickets (either with vendor or directly online) and share tickets with university | 2025-09-16 | Siddhanth Waghmare | could vary
Trains
Name | Due Date | Owner | Notes | Process # | Timeline - Start | Timeline - End
Confirm preferred flight/train option with client | 2025-09-02 | Siddhanth Waghmare | could vary
Collect participant information / passport scans | 2025-09-08 | Siddhanth Waghmare | could vary
Book tickets (either with vendor or directly online) and share tickets with university | 2025-09-16 | Siddhanth Waghmare | could vary
Guides
Name | Due Date | Owner | Notes | Process # | Timeline - Start | Timeline - End
Book dates of preferred guides (Directly or with DMC) | 2025-09-02 | Siddhanth Waghmare
Send draft itinerary to guides/DMC along with the academic objective briefing | 2025-11-01 | Siddhanth Waghmare
Send final itinerary / checklist and PAX info to guides | 2025-11-24 | Siddhanth Waghmare | could vary
Send advance for entrance fees etc. | 2025-11-24 | Siddhanth Waghmare

## Calculations
Operations Process (Proposal to Delivery)
Hotels
Name | Due Date (Rule) | Due Date | Notes | Process # | Timeline - Start | Timeline - End
Block and sign contracts with chosen hotels and procure invoices with payment details | C+1 | 2025-09-02 | As per updated numbers received from the university
Release block for other hotels across locations | C+1 | 2025-09-02
Send advance to chosen hotels: CCA / bank transfer / outward remittance | C+30 | 2025-10-01 | could vary
Collect rooming list from client and send it to hotels | P-15 | 2025-11-16
Flights
Name | Timeframe (Date) | Due Date | Notes | Process # | Timeline - Start | Timeline - End
Confirm preferred flight/train option with client | C+1 | 2025-09-02 | could vary
Collect participant information / passport scans | C+7 | 2025-09-08 | could vary
Book tickets (either with vendor or directly online) and share tickets with university | C+15 | 2025-09-16 | could vary
Trains
Name | Timeframe (Date) | Due Date | Notes | Process # | Timeline - Start | Timeline - End
Confirm preferred flight/train option with client | C+1 | 2025-09-02 | could vary
Collect participant information / passport scans | C+7 | 2025-09-08 | could vary
Book tickets (either with vendor or directly online) and share tickets with university | C+15 | 2025-09-16 | could vary
Guides
Name | Timeframe (Date) | Due Date | Notes | Process # | Timeline - Start | Timeline - End
Book dates of preferred guides (Directly or with DMC) | C+1 | 2025-09-02
Send draft itinerary to guides/DMC along with the academic objective briefing | P-30 | 2025-11-01
Send final itinerary / checklist and PAX info to guides | P-7 | 2025-11-24 | could vary
Send advance for entrance fees etc. | P-7 | 2025-11-24
Formulas:
Due Date = [1]Legend!$C10+1
Due Date = [1]Legend!$C12-15