## Legend
Category-wise steps for confirmed programs
Legend for time-limits within which things need to be done:
Symbol | Meaning | Date | Notes | Milestone
R | stands for date of receiving RFP | 2026-03-01 | Input actual date of receiving RFP | Working on RFP
R+ | stands for no. of days after receiving RFP
S | stands for proposal submission date | 2026-03-15 | Input actual deadline of submitting proposal or Actual date of submitting proposal | Working on RFP
S-/+ | stands for no. of days before/after proposal submission date
C | stands for date of confirmation (for repeat clients, this can be when they tell us group size) | 2026-03-20 | Input actual date of program confirmation | Planning
C+ | stands for no. of days after confirmation/go-ahead received from client
P | stands for program dates | 2026-04-18 | Input actual program start date | Delivery
PE | stands for program end date | 2026-07-31 | Input actual program end date | Delivery
P- | stands for no. of days before program start
P+ | stands for no. of days after the program ends

## Operations Process
Operations Process (Proposal to Delivery)
Action Items while sending proposals
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Ensure sales hand-off template is filled; clarify doubts, if any before working on the proposal | R | 2026-03-01 | Working on RFP
Use itinerary elements template to detail out the requirements | R+1 | 2026-03-02 | Working on RFP
Use vendor template to reach out to DMCs etc. | R+1 | 2026-03-02 | Working on RFP
Decide FOC etc. terms with hotels | R+7 | 2026-03-08 | Working on RFP
Use hotel options, dining options etc. templates to save all information | R+7 | 2026-03-08 | Working on RFP
Document all vendor service limitations and requirements | R+7 | 2026-03-08 | Working on RFP | NEW: Capture luggage transfer limits, group size restrictions, etc.
Verify accommodation standards meet university requirements (private bathrooms, accessibility) | R+7 | 2026-03-08 | Working on RFP | NEW: Based on Cats Hostel Madrid issue
Complete work on costing sheet and proposal formats | R+7 | 2026-03-08 | Working on RFP
Include detailed transportation requirements template (airport transfers, public transit specifications) | S-1 | 2026-03-14 | Working on RFP | NEW: Based on Barcelona transit confusion
Do a thorough proof-reading and cross-checking (with help from another team member) | S-1 | 2026-03-14 | Working on RFP
Ensure block on all hotels and important resources while sending proposals | S | 2026-03-15 | Working on RFP | ensure payments & cancellation are on agreeable terms
Followup with client on the proposal status | S+15 | 2026-03-30 | Working on RFP | could vary
Action Items after program confirmation
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Send advance invoice | P-90 | 2026-01-18 | Planning
Create mastersheet and fill up all tabs with information till date | C+1 | 2026-03-21 | Planning
Implement triple verification system for all bookings | C+3 | 2026-03-23 | Planning | ENHANCED: Real-time tracking
Set up Monday.com collaboration board with university stakeholders | C+3 | 2026-03-23 | Planning | ENHANCED: Real-time tracking
Create and share googlesheets to collect information from client | C+7 | 2026-03-27 | Planning
Prepare orientation ppt / other such information (e.g. language workshop, empathy workshop etc.) | P-30 | 2026-03-19 | Planning
Send balance invoice | P-30 | 2026-03-19 | Planning
Update emergency action plan for the program | P-30 | 2026-03-19 | Planning
Establish clear protocols for mid-program change requests | P-30 | 2026-03-19 | Planning | NEW: Based on OSU budget change requests
Create and share pre-dep information / dossier | P-30 | 2026-03-19 | Planning
Include comprehensive service limitations in student materials | P-30 | 2026-03-19 | Planning | ENHANCED: Luggage specs, transit rules
Create checklist for delivery | P-15 | 2026-04-03 | Delivery
Continue updating mastersheet on regular basis | P-7 | 2026-04-11 | Delivery
Create documentation and communication plan | P-7 | 2026-04-11 | Delivery
Plan and prepare first aid kits and other relevant material specific to programs | P-7 | 2026-04-11 | Delivery
Print checklists and relevant documents | P-15 | 2026-04-17 | Delivery
Note any additional expenses beyond what we have invoiced for | P | 2026-04-11 | Delivery | sometimes things are added even before program
Send payment links to individuals for single supp/extra nights/activities (e.g. baseball match) etc. | P | 2026-04-11 | Delivery | time-frame could vary
Send invoice to client for additional expenses | P+7 | 2026-07-31 | Delivery | Enter Program end date + 7 days
Send thank you notes to partner organizations / companies | P+7 | 2026-07-31 | Delivery | Send thank you notes on the same day of the visit (could vary based on the work load)
Pre-departure planning
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Mandatory vendor service specification documentation | C+45 | 2026-04-15 | Working on RFP | NEW: All limitations documented
Local partner certification training completion | C+45 | 2026-04-15 | Working on RFP | NEW: University program standards
Accessibility assessment for all activities and routes | C+40 | 2026-04-10 | Working on RFP | NEW: San Sebastian route equity issue
Weather contingency planning for all group activities | C+35 | 2026-04-05 | Working on RFP | NEW: San Sebastian dinner issue
Restaurant proximity verification (max 10min walk from accommodations) | C+35 | 2026-04-05 | Working on RFP | NEW: Spain group dinner locations
Triple Verification Protocol
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
First verification: All bookings confirmed with vendors | P-15 | 2026-04-03 | Planning | NEW: Screenshot confirmations required
Second verification: Room counts, amenity specifications | P-7 | 2026-04-11 | Planning | NEW: Private bathroom verification
Third verification: Final headcount updates to all vendors | P-2 | 2026-04-16 | Delivery | NEW: Prevent overbooking issues
Pre-program vendor briefing calls (hotels, transport, guides) | P-2 | 2026-04-16 | Delivery | NEW: 72-hour advance coordination
Transit pass delivery confirmation (24hrs before first use) | P-2 | 2026-04-16 | Delivery | NEW: San Sebastian dinner issue prevention
Driver briefing with printed itineraries in local language | P-2 | 2026-04-16 | Delivery | NEW: Spain bus coordination issue
Hotels
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm room requirement and configurations from client | C+7 | 2026-03-27 | Planning | sometimes this gets modified later
Re-confirm block for chosen hotels across locations (refer notes) | C+1 | 2026-03-21 | Planning | this could involve contracting
Release block for other hotels across locations | C+7 | 2026-03-27 | Planning
Sign contracts with chosen hotels and procure invoices with payment details | C+30 | 2026-04-19 | Planning | hotel's contract format
Send advance to chosen hotels: CCA / bank transfer / outward remittance | C+30 | 2026-04-19 | Delivery | could vary
Collect rooming list from client | P-15 | 2026-04-03 | Delivery
Final enrollment number update to all vendors | P-15 | 2026-04-03 | Delivery | NEW: Tsukuba hotel room issue prevention
Send rooming list to hotels | P-7 | 2026-04-11 | Delivery
Ensure rooms are allocated as per requirement | P-1 | 2026-04-17 | Delivery
Sort out any issues with the rooms in discussion with the duty manager | P | 2026-04-18 | Delivery
Settle balance payments within | P+7 | 2026-08-07 | Delivery | Program end date
Flight/Train bookings
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm preferred flight/train option with client | C+1 | 2026-03-21 | Delivery | could vary
Decide whether you would approach some vendor or book online directly | C+1 | 2026-03-21 | Delivery | could vary
Collect participant information / passport scans | C+7 | 2026-03-27 | Delivery | could vary
Book flights/trains | C+15 | 2026-04-04 | Delivery | could vary
Share tickets with client | P-30 | 2026-03-19 | Delivery
Guides
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Re-confirm block for chosen guides | C+1 | 2026-03-21 | Planning
Send draft itinerary to guides | P-30 | 2026-03-19 | Planning
Academic objectives briefing with all guides and vendors | P-15 | 2026-04-03 | Delivery | NEW: Spain tour guide role clarification
Send final itinerary / checklist and PAX info to guides | P-7 | 2026-04-11 | Delivery | could vary
Send advance for entrance fees etc. | P-1 | 2026-04-17 | Delivery
Be in touch on a daily basis to ensure things are going as per plan / discuss necessary modifications | P | 2026-04-18 | Delivery
Settle accounts | P+7 | 2026-08-07 | Delivery
Meeting Rooms
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Re-confirm exact requirement from client (preferred venue location, purpose of meeting, group size, AV requirement, F&B etc.) | C+1 | 2026-03-21 | Working on RFP
Identify venue as per requirement (if not done at proposal stage) | C+7 | 2026-03-27 | Working on RFP
Finalize venue and block | C+15 | 2026-04-04 | Planning
Pay advance, if needed | P-30 | 2026-03-19 | Delivery | could vary
Re-confirm exact AV etc. requirement from client | P-15 | 2026-04-03 | Delivery
Share AV etc. requirement details to vendor | P-7 | 2026-04-11 | Delivery
Re-confirm all arrangements | P-1 | 2026-04-17 | Delivery
Transport
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm requirement for each destination / specific visits or requirements (e.g. seatbelts, wheelchair acess etc.) | R+1 | 2026-03-02 | Working on RFP
Confirm requirement for each destination / specific visits or requirements (e.g. seatbelts, wheelchair acess etc.) | C | 2026-03-20 | Planning
Contact DMC / local transport vendor with the requirement | R+1 | 2026-03-02 | Working on RFP
Contact DMC / local transport vendor with the requirement | C+1 | 2026-03-21 | Planning
Block chosen vehicles | C+15 | 2026-04-04 | Planning
Send tentative itinerary to check about routes, timings or any specific requirements/issues | P-30 | 2026-03-19 | Planning
Send reminder about flight details to cient | P-30 | 2026-03-19 | Delivery
Receive arrival and departure details from client | P-15 | 2026-04-03 | Delivery
Send updated itinerary and placard | P-7 | 2026-04-11 | Delivery | Asian DMCs require this earlier
Get driver details and confirm he has correct placard and itinerary | P-1 | 2026-04-17 | Delivery
Ensure driver knows the route / addresses and ensure tips are paid at the end | P | 2026-03-19 | Delivery | to be done a day in advance
Ensure tips are paid to each driver on the last day / EOD | P | 2026-03-19 | Delivery
Settle accounts with the transport vendor after checking their invoice | P+7 | 2026-08-07 | Delivery | if any discrepancy, get it sorted
Meals
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm meal requirements to be included | C | 2026-03-20 | Planning
Research appropriate options in each destination (if not done already) | C+7 | 2026-03-27 | Planning | sometimes we have specific seating requirement
Contact shortlisted venues to get availability, rates and menu details | C+15 | 2026-04-04 | Planning
Finalilze and block chosen venues | C+30 | 2026-04-19 | Delivery | sometimes client approval is needed
Pay advance, if needed | P-30 | 2026-03-19 | Delivery
Send dietary restrictions | P-15 | 2026-04-03 | Delivery
Finalize menu with dietary restrictions | P-7 | 2026-04-11 | Delivery | sometimes client approval is needed
Reconfirm seating and menu | P-1 | 2026-04-17 | Delivery
Balance payment | P | 2026-04-18 | Delivery
Immersions
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm criteria for immersions in each location | C | 2026-03-20 | Working on RFP
Research appropriate options in each destination (if not done already) | C+7 | 2026-03-27 | Working on RFP | sometimes we have specific seating requirement
Contact shortlisted options to get availability, rates and activity details | C+15 | 2026-04-04 | Planning
Finalilze and block chosen options with any specific instruction (e.g. specific guides, atomic bomb survivor etc.) | C+30 | 2026-04-19 | Planning | sometimes client approval is needed
Pay advance, if needed | P-30 | 2026-03-19 | Planning
Send/collect required info (e.g. PAX details) | P-7 | 2026-04-11 | Delivery | time-frame could vary
Reconfirm all arrangements | P-1 | 2026-04-17 | Delivery
Balance payment, if relevant | P | 2026-04-18 | Delivery
Org Visits
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Identify ideal org visits in each destination | C+15 | 2026-04-04 | Planning
Ensure relevant team members reach out to the point of contact | C+30 | 2026-04-19 | Planning | could continue over months
Collect relevant info to be shared (e.g. bio book) from client | P-30 | 2026-03-19 | Delivery
Finalize visits in discussion with the client | P-30 | 2026-03-19 | Delivery
Get logistical contact at each org | P-30 | 2026-03-19 | Delivery
Send / collect relevant info (address, timings, entry/security procedure etc.) | P-15 | 2026-04-03 | Delivery
Reconfirm visit | P-15 | 2026-04-17 | Delivery
Ensure group reaches 10 mins. before meeting time and driver is ready at the end of the meeting | P | 2026-04-18 | Delivery
Give gifts to our contacts | P | 2026-04-18 | Delivery
Send thank you notes to org contacts | P | 2026-04-18 | Delivery | within 24 hours of visit
Collect feedback, if relevant | P+7 | 2026-08-07 | Delivery
Projects
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm criteria for projects | C | 2026-03-20 | Workng on RFP
Identify relevant orgs and contact them with a template email with requirements | C+15 | 2026-04-04 | Workng on RFP
Shortlist relevant / interested orgs and share their details to the client | C+30 | 2026-04-19 | Workng on RFP | this might take longer
Discuss project scope and help orgs draft project description | P-60 | 2026-02-17 | Workng on RFP | time-frame could vary
Finalize project description and share with client | P-30 | 2026-03-19 | Planning | time-frame could vary
Ensure org is ready to host group | P-15 | 2026-04-03 | Planning
Send/collect relevant info and share with group (address, timings, specific procedure for first day etc.) | P-7 | 2026-04-11 | Delivery
Reconfirm all arrangements | P-1 | 2026-04-17 | Delivery
Accompany group to org location and ensure they are well settled | P | 2026-04-18 | Delivery
Be in touch with the group and org throughout the program | P | 2026-04-18 | Delivery
Collect feedback | P+7 | 2026-08-07 | Delivery
Daily Operations Protocol
Program Delivery
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Evening debrief meetings with APM and faculty | Daily | - | Delivery | NEW: Address emerging issues
Vendor reconfirmation for next day activities | Daily | - | Delivery | NEW: Prevent last-minute surprises
Weather and contingency plan review | Daily | - | Delivery | NEW: Proactive planning
Group cohesion monitoring and accommodation equity checks | Daily | - | Delivery | NEW: Prevent split group issues
Enhanced Safety & Communication
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
WhatsApp group management (separate faculty/student groups) | Real-time | - | Delivery | ENHANCED: Improved communication
Daily safety protocol verification with drivers | Daily | - | Delivery | NEW: Spain bus safety incident prevention
Emergency transportation budget activation protocols | As needed | - | Delivery | NEW: Weather-related backup plans
Enhanced Quality Assurance
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Immediate debrief with all stakeholders within 48 hours | P+15 | 2026-08-15 | Delivery | NEW: Rapid issue identification
Service failure compensation processing | P+15 | 2026-08-15 | Delivery | NEW: Proactive client relations
Local partner performance evaluation | P+15 | 2026-08-15 | Delivery | NEW: Continuous improvement
Process improvement documentation | P+15 | 2026-08-15 | Delivery | NEW: Learning integration
Client satisfaction follow-up call | P+15 | 2026-08-15 | Delivery | NEW: Relationship management
Document Version History
Modified By | Created on | Modified On |  | Comments | Version #
Siddhanth Waghmare | 2025-01-22 | 2025-01-22 |  | Updated a checklist for End-To-End Operations Process (Proposal to Delivery); created excel sheet from Monday board (Operations Process) | 1
Siddhanth Waghmare | - | 2025-07-07 |  | This upgraded checklist incorporates specific learnings from the Ohio State KSA Spain and JADE programs to prevent recurrence of identified issues while maintaining operational excellence. | 2
Note on E209: Siddhanth Waghmare: KEY SYSTEM ENHANCEMENTS 1. Booking Management System • Triple verification protocol for all reservations • Automated alerts for enrollment changes • Screenshot confirmation requirements • Penalty clauses in vendor contracts 2. Communication Framework • Mandatory 72-hour vendor briefings • Monday.com real-time collaboration • Written confirmation protocols • Local language documentation requirements 3. Quality Assurance Protocol • 52-point pre-departure checklist • Daily operations monitoring • Service failure compensation framework • Continuous improvement documentation 4. Emergency Response Enhancement • Weather contingency planning • Emergency transportation budget • Immediate escalation procedures • 24/7 management access ________________________________________ COMPLIANCE CHECKPOINTS New Mandatory Checkpoints Based on OSU Issues: ✓ Accommodation Standards Verification • Private bathroom confirmation • Accessibility compliance • Group cohesion maintenance ✓ Transportation Coordination • Driver briefing completion • Safety protocol acknowledgment • Itinerary delivery confirmation ✓ Vendor Service Specifications • Size/weight limitations documented • Service restrictions communicated • Academic objectives clarified ✓ Timeline Management • Deliverable scheduling verification • Weather contingency activation • Change request protocol adherence

## Faculty Led Programs
Operations Process (Proposal to Delivery)
Action Items while sending proposals
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Ensure sales hand-off template is filled; clarify doubts, if any before working on the proposal | R | 2026-03-01 | Working on RFP
Use itinerary elements template to detail out the requirements | R+1 | 2026-03-02 | Working on RFP
Get quotes from DMCs/hotels for program dates | R+1 | 2026-03-02 | Working on RFP | Using vendor templates
Finalize hotel options for the proposal | R+7 | 2026-03-08 | Working on RFP | Using hotel sheet template
Complete and review the costing sheet and proposal | R+7 | 2026-03-08 | Working on RFP | Use formats
Block all proposed hotels and guides | S | 2026-03-15 | Working on RFP | ensure payments & cancellation are on agreeable terms
Followup with client/sales on the proposal status to release or keep the blocks | S+15 | 2026-03-30 | Working on RFP | Proposal confirmation timeline could vary
Action Items after proposal is won
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Sign contracts with hotels and DMCs | P-90 | 2026-01-18 | Planning | timeframe could vary
Followup with client/sales on program confirmation date | P-90 | 2026-01-18 | Planning | timeframe could vary
Action Items after program confirmation
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Send deposit invoice to university | P-90 | 2026-01-18 | Planning | Check proposal terms and conditions
Create mastersheet | C+1 | 2026-03-21 | Planning | Use template and fill information on an on-going basis
Set up Monday.com/google sheet for collaboration with all university stakeholders | C+3 | 2026-03-23 | Planning | ENHANCED: Real-time tracking
Share participant data template to collect information (including scanned passport copies) | C+7 | 2026-03-27 | Planning | Use participant data template #to client
Prepare for in-person/online program orientation and safety briefing | P-30 | 2026-03-19 | Planning | Refer to India orientation PPT
Send balance invoice to university | P-30 | 2026-03-19 | Planning
Get confirmation on final service requirements from university |  |  | Planning | Confirm final group size, hotel blocks, transport, guides, meals, academic content and cultural immersions
Send final program services agreement |  | 2026-03-19 | Planning
Create and share pre-departure guide | P-30 | 2026-03-19 | Planning | Refer to standard pre dep template
Create checklist for delivery | P-15 | 2026-04-03 | Delivery | Refer to mastersheet for template
Plan and prepare first aid kits and other relevant material specific to programs | P-7 | 2026-04-11 | Delivery
Print checklists and relevant documents | P-15 | 2026-04-17 | Delivery
Send post program invoice to the university | P+7 | 2026-07-31 | Delivery | Enter Program end date + 7 days
Send thank you notes to partner organizations / companies | P+7 | 2026-07-31 | Delivery | Send thank you notes on the same day of the visit (could vary based on the work load)
Pre-departure planning
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Mandatory vendor service specification documentation | C+45 | 2026-04-15 | Working on RFP | NEW: All limitations documented
Complete program orientation for guides and local partners | C+45 | 2026-04-15 | Working on RFP | Brief them about Authentica standards
Triple Verification Protocol
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Verify pre-program delivery checklist | P-7 | 2026-04-11 | Planning | Refer template
Hotels
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Block and sign contracts with chosen hotels and procure invoices with payment details | C+1 | 2026-03-21 | Planning | As per updated numbers received from the university
Release block for other hotels across locations | C+1 | 2026-03-21 | Planning
Send advance to chosen hotels: CCA / bank transfer / outward remittance | C+30 | 2026-04-19 | Delivery | could vary
Collect rooming list from client and send it to hotels | P-15 | 2026-04-03 | Delivery
Flight/Train bookings
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm preferred flight/train option with client | C+1 | 2026-03-21 | Delivery | could vary
Collect participant information / passport scans | C+7 | 2026-03-27 | Delivery | could vary
Book tickets (either with vendor or directly online) and share tickets with university | C+15 | 2026-04-04 | Delivery | could vary
Guides
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Book dates of preferred guides (Directly or with DMC) | C+1 | 2026-03-21 | Planning
Send draft itinerary to guides/DMC along with the academic objective briefing | P-30 | 2026-03-19 | Planning
Send final itinerary / checklist and PAX info to guides | P-7 | 2026-04-11 | Delivery | could vary
Send advance for entrance fees etc. | P-7 | 2026-04-11 | Delivery
Meeting Rooms
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm exact requirement from client (preferred venue location, purpose of meeting, group size, AV requirement, F&B etc.) | C+1 | 2026-03-21 | Working on RFP
Identify, block and finalize venue | C+15 | 2026-04-04 | Planning
Pay advance, if needed | P-30 | 2026-03-19 | Delivery | could vary
Re-confirm exact requirements from university and share it with vendors | P-15 | 2026-04-03 | Delivery
Transport
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm requirement for each destination / specific visits or requirements (e.g. seatbelts, wheelchair acess etc.) and share with vendors/DMC | C | 2026-03-20 | Planning
Send transport/DMC itinerary to check about routes, timings or any specific requirements/issues | P-30 | 2026-03-19 | Planning
Share arrival and departure schedule to university and share it with vendors/DMC | P-15 | 2026-04-03 | Delivery | As per the mastersheet template
Send final itinerary and placard | P-7 | 2026-04-11 | Delivery | Asian DMCs require this earlier
Meals
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm meal requirements to be included | C | 2026-03-20 | Planning
Research appropriate options in each destination (if not done already) | C+7 | 2026-03-27 | Planning | sometimes we have specific seating requirement
Contact shortlisted venues to get availability, rates and menu details | C+15 | 2026-04-04 | Planning
Finalilze and block chosen venues | C+30 | 2026-04-19 | Delivery | sometimes client approval is needed
Pay advance, if needed | P-30 | 2026-03-19 | Delivery
Send dietary restrictions | P-15 | 2026-04-03 | Delivery
Finalize menu with dietary restrictions | P-7 | 2026-04-11 | Delivery | sometimes client approval is needed
Reconfirm seating and menu | P-1 | 2026-04-17 | Delivery
START FROM HERE
Immersions
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Finalilze and block chosen options with any specific instruction (e.g. specific guides, atomic bomb survivor etc.) | C+15 | 2026-04-04 | Planning | sometimes client approval is needed
Pay advance, if needed | P-30 | 2026-03-19 | Planning
Org Visits
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Brief PDs/Content partners regarding program theme and requirements | C+15 | 2026-04-04 | Planning
Collect relevant info to be shared (e.g. bio book) from client | P-30 | 2026-03-19 | Delivery
Finalize visits in discussion with the client and PDs | P-30 | 2026-03-19 | Delivery
Get logistical contacts from PDs at for each visit | P-30 | 2026-03-19 | Delivery
Co-ordinate with organizations about the visit (timings, address, meals, security protocols like passports, roster sheet, license plate) | P-15 | 2026-04-03 | Delivery
Plan and procure gifts for organization visits | P-30 | 2026-03-19 | Delivery
Post Program Action items
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Settle balance payments of all vendors
Submit expense report to HQ
Upload media to zoho drive
Immediate debrief with all stakeholders within 48 hours | P+15 | 2026-08-15 | Delivery | NEW: Rapid issue identification
Service failure compensation processing | P+15 | 2026-08-15 | Delivery | NEW: Proactive client relations
Local partner performance evaluation | P+15 | 2026-08-15 | Delivery | NEW: Continuous improvement
Process improvement documentation | P+15 | 2026-08-15 | Delivery | Use learnings template in Mastersheet
Client satisfaction follow-up call | P+15 | 2026-08-15 | Delivery | NEW: Relationship management
Document Version History
Modified By | Created on | Modified On |  | Comments | Version #
Siddhanth Waghmare | 2025-01-22 | 2025-01-22 |  | Updated a checklist for End-To-End Operations Process (Proposal to Delivery); created excel sheet from Monday board (Operations Process) | 1
Siddhanth Waghmare | - | 2025-07-07 |  | This upgraded checklist incorporates specific learnings from the Ohio State KSA Spain and JADE programs to prevent recurrence of identified issues while maintaining operational excellence. | 2
Sid, Vedanth and VL |  | 2026-03-24 |  | Modified the list for specific action oriented goals. Separated action items Vs quality checklist | 3
Note on E124: Siddhanth Waghmare: KEY SYSTEM ENHANCEMENTS 1. Booking Management System • Triple verification protocol for all reservations • Automated alerts for enrollment changes • Screenshot confirmation requirements • Penalty clauses in vendor contracts 2. Communication Framework • Mandatory 72-hour vendor briefings • Monday.com real-time collaboration • Written confirmation protocols • Local language documentation requirements 3. Quality Assurance Protocol • 52-point pre-departure checklist • Daily operations monitoring • Service failure compensation framework • Continuous improvement documentation 4. Emergency Response Enhancement • Weather contingency planning • Emergency transportation budget • Immediate escalation procedures • 24/7 management access ________________________________________ COMPLIANCE CHECKPOINTS New Mandatory Checkpoints Based on OSU Issues: ✓ Accommodation Standards Verification • Private bathroom confirmation • Accessibility compliance • Group cohesion maintenance ✓ Transportation Coordination • Driver briefing completion • Safety protocol acknowledgment • Itinerary delivery confirmation ✓ Vendor Service Specifications • Size/weight limitations documented • Service restrictions communicated • Academic objectives clarified ✓ Timeline Management • Deliverable scheduling verification • Weather contingency activation • Change request protocol adherence

## Internships
Operations Process (Proposal to Delivery)
Action Items while sending proposals
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Ensure sales hand-off template is filled; clarify doubts, if any before working on the proposal | R | 2026-03-01 | Working on RFP
Use itinerary elements template to detail out the requirements | R+1 | 2026-03-02 | Working on RFP
Get quotes from DMCs/hotels for program dates | R+1 | 2026-03-02 | Working on RFP | Using vendor templates
Finalize hotel options for the proposal | R+7 | 2026-03-08 | Working on RFP | Using hotel sheet template
Complete and review the costing sheet and proposal | R+7 | 2026-03-08 | Working on RFP | Use formats
Block all proposed hotels and guides | S | 2026-03-15 | Working on RFP | ensure payments & cancellation are on agreeable terms
Followup with client/sales on the proposal status to release or keep the blocks | S+15 | 2026-03-30 | Working on RFP | Proposal confirmation timeline could vary
Action Items after proposal is won
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Sign contracts with hotels and DMCs | P-90 | 2026-01-18 | Planning | timeframe could vary
Followup with client/sales on program confirmation date | P-90 | 2026-01-18 | Planning | timeframe could vary
Action Items after program confirmation
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Send deposit invoice to university | P-90 | 2026-01-18 | Planning | Check proposal terms and conditions
Create mastersheet | C+1 | 2026-03-21 | Planning | Use template and fill information on an on-going basis
Set up Monday.com/google sheet for collaboration with all university stakeholders | C+3 | 2026-03-23 | Planning | ENHANCED: Real-time tracking
Share participant data template to collect information (including scanned passport copies) | C+7 | 2026-03-27 | Planning | Use participant data template #to client
Prepare for in-person/online program orientation and safety briefing | P-30 | 2026-03-19 | Planning | Refer to India orientation PPT
Send balance invoice to university | P-30 | 2026-03-19 | Planning
Get confirmation on final service requirements from university |  |  | Planning | Confirm final group size, hotel blocks, transport, guides, meals, academic content and cultural immersions
Send final program services agreement |  | 2026-03-19 | Planning
Create and share pre-departure guide | P-30 | 2026-03-19 | Planning | Refer to standard pre dep template
Create checklist for delivery | P-15 | 2026-04-03 | Delivery | Refer to mastersheet for template
Plan and prepare first aid kits and other relevant material specific to programs | P-7 | 2026-04-11 | Delivery
Print checklists and relevant documents | P-15 | 2026-04-17 | Delivery
Send post program invoice to the university | P+7 | 2026-07-31 | Delivery | Enter Program end date + 7 days
Send thank you notes to partner organizations / companies | P+7 | 2026-07-31 | Delivery | Send thank you notes on the same day of the visit (could vary based on the work load)
Pre-departure planning
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Mandatory vendor service specification documentation | C+45 | 2026-04-15 | Working on RFP | NEW: All limitations documented
Complete program orientation for guides and local partners | C+45 | 2026-04-15 | Working on RFP | Brief them about Authentica standards
Triple Verification Protocol
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Verify pre-program delivery checklist | P-7 | 2026-04-11 | Planning | Refer template
Hotels
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Block and sign contracts with chosen hotels and procure invoices with payment details | C+1 | 2026-03-21 | Planning | As per updated numbers received from the university
Release block for other hotels across locations | C+1 | 2026-03-21 | Planning
Send advance to chosen hotels: CCA / bank transfer / outward remittance | C+30 | 2026-04-19 | Delivery | could vary
Collect rooming list from client and send it to hotels | P-15 | 2026-04-03 | Delivery
Flight/Train bookings
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm preferred flight/train option with client | C+1 | 2026-03-21 | Delivery | could vary
Collect participant information / passport scans | C+7 | 2026-03-27 | Delivery | could vary
Book tickets (either with vendor or directly online) and share tickets with university | C+15 | 2026-04-04 | Delivery | could vary
Guides
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Book dates of preferred guides (Directly or with DMC) | C+1 | 2026-03-21 | Planning
Send draft itinerary to guides/DMC along with the academic objective briefing | P-30 | 2026-03-19 | Planning
Send final itinerary / checklist and PAX info to guides | P-7 | 2026-04-11 | Delivery | could vary
Send advance for entrance fees etc. | P-7 | 2026-04-11 | Delivery
Meeting Rooms
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm exact requirement from client (preferred venue location, purpose of meeting, group size, AV requirement, F&B etc.) | C+1 | 2026-03-21 | Working on RFP
Identify, block and finalize venue | C+15 | 2026-04-04 | Planning
Pay advance, if needed | P-30 | 2026-03-19 | Delivery | could vary
Re-confirm exact requirements from university and share it with vendors | P-15 | 2026-04-03 | Delivery
Transport
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm requirement for each destination / specific visits or requirements (e.g. seatbelts, wheelchair acess etc.) and share with vendors/DMC | C | 2026-03-20 | Planning
Send transport/DMC itinerary to check about routes, timings or any specific requirements/issues | P-30 | 2026-03-19 | Planning
Share arrival and departure schedule to university and share it with vendors/DMC | P-15 | 2026-04-03 | Delivery | As per the mastersheet template
Send final itinerary and placard | P-7 | 2026-04-11 | Delivery | Asian DMCs require this earlier
Meals
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm meal requirements to be included | C | 2026-03-20 | Planning
Research appropriate options in each destination (if not done already) | C+7 | 2026-03-27 | Planning | sometimes we have specific seating requirement
Contact shortlisted venues to get availability, rates and menu details | C+15 | 2026-04-04 | Planning
Finalilze and block chosen venues | C+30 | 2026-04-19 | Delivery | sometimes client approval is needed
Pay advance, if needed | P-30 | 2026-03-19 | Delivery
Send dietary restrictions | P-15 | 2026-04-03 | Delivery
Finalize menu with dietary restrictions | P-7 | 2026-04-11 | Delivery | sometimes client approval is needed
Reconfirm seating and menu | P-1 | 2026-04-17 | Delivery
START FROM HERE
Immersions
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Finalilze and block chosen options with any specific instruction (e.g. specific guides, atomic bomb survivor etc.) | C+15 | 2026-04-04 | Planning | sometimes client approval is needed
Pay advance, if needed | P-30 | 2026-03-19 | Planning
Org Visits
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Brief PDs/Content partners regarding program theme and requirements | C+15 | 2026-04-04 | Planning
Collect relevant info to be shared (e.g. bio book) from client | P-30 | 2026-03-19 | Delivery
Finalize visits in discussion with the client and PDs | P-30 | 2026-03-19 | Delivery
Get logistical contacts from PDs at for each visit | P-30 | 2026-03-19 | Delivery
Co-ordinate with organizations about the visit (timings, address, meals, security protocols like passports, roster sheet, license plate) | P-15 | 2026-04-03 | Delivery
Plan and procure gifts for organization visits | P-30 | 2026-03-19 | Delivery
Projects for Internships
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Confirm criteria for projects | C | 2026-03-20 | Workng on RFP
Identify relevant orgs and contact them with a template email with requirements | C+15 | 2026-04-04 | Workng on RFP
Shortlist relevant / interested orgs and share their details to the client | C+30 | 2026-04-19 | Workng on RFP | this might take longer
Discuss project scope and help orgs draft project description | P-60 | 2026-02-17 | Workng on RFP | time-frame could vary
Finalize project description and share with client | P-30 | 2026-03-19 | Planning | time-frame could vary
Ensure org is ready to host group | P-15 | 2026-04-03 | Planning
Send/collect relevant info and share with group (address, timings, specific procedure for first day etc.) | P-7 | 2026-04-11 | Delivery
Reconfirm all arrangements | P-1 | 2026-04-17 | Delivery
Accompany group to org location and ensure they are well settled | P | 2026-04-18 | Delivery
Be in touch with the group and org throughout the program | P | 2026-04-18 | Delivery
Collect feedback | P+7 | 2026-08-07 | Delivery
Post Program Action items
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Settle balance payments of all vendors
Submit expense report to HQ
Upload media to zoho drive
Immediate debrief with all stakeholders within 48 hours | P+15 | 2026-08-15 | Delivery | NEW: Rapid issue identification
Service failure compensation processing | P+15 | 2026-08-15 | Delivery | NEW: Proactive client relations
Local partner performance evaluation | P+15 | 2026-08-15 | Delivery | NEW: Continuous improvement
Process improvement documentation | P+15 | 2026-08-15 | Delivery | Use learnings template in Mastersheet
Client satisfaction follow-up call | P+15 | 2026-08-15 | Delivery | NEW: Relationship management
Document Version History
Modified By | Created on | Modified On |  | Comments | Version #
Siddhanth Waghmare | 2025-01-22 | 2025-01-22 |  | Updated a checklist for End-To-End Operations Process (Proposal to Delivery); created excel sheet from Monday board (Operations Process) | 1
Siddhanth Waghmare | - | 2025-07-07 |  | This upgraded checklist incorporates specific learnings from the Ohio State KSA Spain and JADE programs to prevent recurrence of identified issues while maintaining operational excellence. | 2
Sid, Vedanth and VL |  | 2026-03-24 |  | Modified the list for specific action oriented goals. Separated action items Vs quality checklist | 3
Note on E138: Siddhanth Waghmare: KEY SYSTEM ENHANCEMENTS 1. Booking Management System • Triple verification protocol for all reservations • Automated alerts for enrollment changes • Screenshot confirmation requirements • Penalty clauses in vendor contracts 2. Communication Framework • Mandatory 72-hour vendor briefings • Monday.com real-time collaboration • Written confirmation protocols • Local language documentation requirements 3. Quality Assurance Protocol • 52-point pre-departure checklist • Daily operations monitoring • Service failure compensation framework • Continuous improvement documentation 4. Emergency Response Enhancement • Weather contingency planning • Emergency transportation budget • Immediate escalation procedures • 24/7 management access ________________________________________ COMPLIANCE CHECKPOINTS New Mandatory Checkpoints Based on OSU Issues: ✓ Accommodation Standards Verification • Private bathroom confirmation • Accessibility compliance • Group cohesion maintenance ✓ Transportation Coordination • Driver briefing completion • Safety protocol acknowledgment • Itinerary delivery confirmation ✓ Vendor Service Specifications • Size/weight limitations documented • Service restrictions communicated • Academic objectives clarified ✓ Timeline Management • Deliverable scheduling verification • Weather contingency activation • Change request protocol adherence

## QC Checklist
Action Items while sending proposals
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Document all vendor service limitations and requirements | R+7 | 2026-03-08 | Working on RFP | NEW: Capture luggage transfer limits, group size restrictions, etc.
Verify accommodation standards meet university requirements (private bathrooms, accessibility) | R+7 | 2026-03-08 | Working on RFP | NEW: Based on Cats Hostel Madrid issue
Include detailed transportation requirements template (airport transfers, public transit specifications) | S-1 | 2026-03-14 | Working on RFP | NEW: Based on Barcelona transit confusion
Implement triple verification system for all bookings | C+3 | 2026-03-23 | Planning | ENHANCED: Real-time tracking
Establish clear protocols for mid-program change requests | P-30 | 2026-03-19 | Planning | NEW: Based on OSU budget change requests Add this point to services agreement
Include comprehensive service limitations in student materials | P-30 | 2026-03-19 | Planning | ENHANCED: Luggage specs, transit rules Add this point to services agreement
Accessibility assessment for all activities and routes | C+40 | 2026-04-10 | Working on RFP | NEW: San Sebastian route equity issue
Weather contingency planning for all group activities | C+35 | 2026-04-05 | Working on RFP | NEW: San Sebastian dinner issue
Restaurant proximity verification (max 10min walk from accommodations) | C+35 | 2026-04-05 | Working on RFP | NEW: Spain group dinner locations
Continue updating mastersheet on regular basis | P-7 | 2026-04-11 | Delivery
Note any additional expenses beyond what we have invoiced for | P | 2026-04-11 | Delivery | Update the "post program invoice" tab in the mastersheet
Send payment links to individuals for single supp/extra nights/activities (e.g. baseball match) etc. | P | 2026-04-11 | Delivery | time-frame could vary
Triple Verification Protocol
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
First verification: All bookings confirmed with vendors | P-15 | 2026-04-03 | Planning | NEW: Screenshot confirmations required
Second verification: Room counts, amenity specifications | P-7 | 2026-04-11 | Planning | NEW: Private bathroom verification
Third verification: Final headcount updates to all vendors | P-2 | 2026-04-16 | Delivery | NEW: Prevent overbooking issues
Pre-program vendor briefing calls (hotels, transport, guides) | P-2 | 2026-04-16 | Delivery | NEW: 72-hour advance coordination
Transit pass delivery confirmation (24hrs before first use) | P-2 | 2026-04-16 | Delivery | NEW: San Sebastian dinner issue prevention
Driver briefing with printed itineraries in local language | P-2 | 2026-04-16 | Delivery | NEW: Spain bus coordination issue
Hotels
Ensure rooms are allocated as per requirement and sort out any issues with the rooms in discussion with the duty manager | P-1 | 2026-04-17 | Delivery
Guides
Be in touch on a daily basis to ensure things are going as per plan / discuss necessary modifications | P | 2026-04-18 | Delivery
Meeting Rooms
Re-confirm all arrangements | P-1 | 2026-04-17 | Delivery
Transport
Get driver details and confirm he has correct placard and itinerary | P-1 | 2026-04-17 | Delivery
Ensure driver knows the route / addresses and ensure tips are paid at the end | P | 2026-03-19 | Delivery | to be done a day in advance
Ensure tips are paid to each driver on the last day / EOD | P | 2026-03-19 | Delivery
Immersions
Reconfirm all arrangements | P-1 | 2026-04-17 | Delivery
Org Visits
Reconfirm visit | P-15 | 2026-04-17 | Delivery
Ensure group reaches 10 mins. before meeting time and driver is ready at the end of the meeting | P | 2026-04-18 | Delivery
Give gifts to our contacts | P | 2026-04-18 | Delivery
Send thank you notes to org contacts and collect feedback (if any) | P | 2026-04-18 | Delivery | within 24 hours of visit
Daily Operations Protocol
Program Delivery
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
Evening debrief meetings with APM and faculty | Daily | - | Delivery | NEW: Address emerging issues
Vendor reconfirmation for next day activities | Daily | - | Delivery | NEW: Prevent last-minute surprises
Weather and contingency plan review | Daily | - | Delivery | NEW: Proactive planning
Group cohesion monitoring and accommodation equity checks | Daily | - | Delivery | NEW: Prevent split group issues
Enhanced Safety & Communication
Name | Timeframe (Date) | Timeframe (Date) | Milestone | Notes | Process # | Timeline - Start | Timeline - End
WhatsApp group management (separate faculty/student groups) | Real-time | - | Delivery | ENHANCED: Improved communication
Daily safety protocol verification with drivers | Daily | - | Delivery | NEW: Spain bus safety incident prevention
Emergency budget activation protocols | As needed | - | Delivery | NEW: Weather-related backup plans